## Group member 4
To-do list
To be completed by: |  | 2025-10-09 |  | Name: Esfar, Justin, Sayantan, Fahim, Yousuf
Deadline: |  | 2025-10-10 |  | Date: 09/30/2025
Chapter 4 and 5
% done | Phase | Start By | Original Due By2 | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2025-09-30 | 2025-10-02 | 2025-10-09 |  | Communicate as a group to review the professor’s assignment instructions. Assign roles (e.g. drafting individual's propositions, setting deadlines, undertanding topics, who writes explanations, who manages GitHub). Agree on internal deadlines before the official due date.
95% | Research & Preparation | 2025-09-30 | 2025-10-04 | 2025-10-06 |  | All members read through Chapter 4 (Subqueries) and Chapter 5 (Table Expressions). As a group, review provided SQL examples from the textbook and exercises. Load the WideWorldImporters database in DBeaver/Azure Data Studio. Test sample queries to confirm database is working for everyone.
88% | Drafting Propositions | 2025-10-04 | 2025-10-04 | 2025-10-05 |  | Brainstorm 10 different propositions (2 per group member). Ensure no duplication from examples, but stay aligned with subqueries and table expressions. Collect propositions into a shared document for review.
95% | Writing Queries | 2025-10-05 | 2025-10-07 | 2025-10-08 |  | Each member writes SQL queries for their assigned propositions. Share queries with the group for testing and corrections. Make sure queries run correctly in WideWorldImporters.
90% | Explanations | 2025-10-07 | 2025-10-08 | 2025-10-09 |  | clear explanations for each proposition: How it was done Why it’s useful Business importance Consolidate queries and explanations into one
95% | Group Presentation | 2025-10-09 | 2025-10-10 | 2025-10-10 |  | Record a walkthrough of all 10 propositions and queries as a team. Each member presents their part of the work in the video.