## Group member 4
To-do list
To be completed by: |  | 2025-10-10 |  | Name: Fahim Tanvir
Deadline: |  | 2025-10-10 |  | Date: 09/30/2025
Chapter 4 and 5
% done | Phase | Start By | Original Due By2 | Revised Due By(and completed at) | Number Of Days to complete | Revision Notes
100% | Setting it up | 2025-09-26 | 2025-09-30 | 2025-09-30 | 1 | Set up github repo, assign collaborate roles to groupmates and look at the assignment directions.
100% | Planning | 2025-09-26 | 2025-09-30 | 2025-09-30 |  | Find partner for the video and plan out schedule to communicate with them about propositions and video. Assign another pair and individual person as well.
100% | Drafting | 2025-10-04 | 2025-10-04 | 2025-10-05 | 2 | Look at chapters 4 and 5 and past lectures regarding them to form 10 propositions.
100% | Writing Queries | 2025-09-30 | 2025-10-02 | 2025-10-06 | 3 | Create 10 propositions with partner(Esfar) and test each of them on microsoft sql management tool and dbeaver. Get Justin for Azure testing.
100% | Recording videos explaining query | 2025-10-07 | 2025-10-08 | 2025-10-08 | 1 | Record myself with my partner esfar in regards to our videos introduction along with outro regarding NACE competancies.
100% | Record video with partner | 2025-10-03 | 2025-10-06 | 2025-10-07 | 1 | Record myself with my partner esfar in regards to our videos introduction along with outro regarding NACE competancies.
100% | Finalize video | 2025-10-09 | 2025-10-09 | 2025-10-10 | 1 | Edit and compile all of the videos me and Esfar made into using video editing tool(OpenShot).
100% | Submit | 2025-10-10 | 2025-10-10 | 2025-10-10 | 1 | Wait for everyone to finish and make the 3 teammates check eachothers work as a final check. I will submit for the team at 10:00 pm on the submission date and add the Proffesor to the git.